## Overview
fault tree above | translated to | spreadsheet | additions | below as an | example:
Ref ID |  | Ref ID |  |  |  | Overall | Mitigation/Warning | Post-Mitigation
| Intermediate Event |  | Basic Event | Likelihood (1-5) | Consequence (1-5) |  |  | Likelihood | Consequence
EX-1 | All Bulbs burnt | &EX-1.1 | Lamp 1 burned | 2 | 3 | 6 | Alarm when bulb goes out | 1 | 3
|  | &EX-1.2 | Lamp 2 burned | 2 | 3 | 6 | Alarm when bulb goes out | 1 | 3
EX-2 |  | EX-2.1 | Switch Failed | 2 | 4 | 8 | mitigation | 1 | 3
EX-3 | No Voltage at Input | OEX-3.1 | No V in network | 1 | 3 | 3 | mitigation | 1 | 2
|  | OEX-3.2 | Fuse burned | 2 | 3 | 6 | mitigation | 1 | 3
Likelihood from 1-5:
1: Not likely (P < 20%)
2: Low likelihood (20% <= P < 40%)
3: Likely (40% <= P < 60%)
4: Highly likely (60% <= P < 80%)
5: Near certainty (P >= 80%)
Consequence from 1-5:
Provide simple, basic mitigation/warning where relevant (no details needed), and add likelihood and consequence numbers post-mitigation.
The numbers are generally only required for basic events, but you can choose to add columns to add likelihood and consequence numbers for the intermediate events if you wish.
The spreadsheet is designed to be added to both a 5x5 risk matrix and a fault tree. Therefore, the organization is according to the overall event, intermediate event, and the basic event. The overall event refers to a major risk/failure to your overall system, the intermediate event outlines a subsystem of sorts, and the basic event is down to the smallest level. You don’t have to categorize the risks in this way, and only have one overall event with all basic events under it if it makes more sense for your system. For each basic event you input, add an O (or) or & (and) and group each together. Following is a very basic fault tree, and you can google NASA’s basic 5x5 risk matrix if you are not familiar with it:

## Habitat
Ref ID |  | Ref ID |  |  |  | Overall | Mitigation/Warning | Post-Mitigation
| Intermediate Event |  | Basic Event | Likelihood (1-5) | Consequence (1-5) |  |  | Likelihood | Consequence
SH-1 | Power system Failure | SH-1.1 | Solar panel failure | 1 | 1 | 1 | Multiple Solar Panel Systems for Redundancy
|  | SH-1.2 | Battery failure | 1 | 1 | 1 | Multiple Battery Locations for Redundancy
|  | SH-1.3 | Short circuit | 1 | 1 | 1 | Proper Maintenance of Electrical Systems
SH-2 | Elecrical Fire | SH-2.1 | Short circuit/sparking | 1 | 4 | 4 | FPE/ Fire prevention systems. Ability to shutdown electricity to individual habitats in event of emergency
|  | SH-2.2 | Component Failure | 1 | 4 | 4 | Active inspection of components for signs of wear
SH-3 | Depressurization Event |  |  |  |  | 0
|  | SH-3.1 | Minor Leak | 3 | 2 | 6 | Readily repairable, quality control, regular monitoring of system pressure, maintenance
|  | SH-3.2 | Intermediate Leak | 1 | 4 | 4 | Evacuation procedures, sealing off depressurized area, may or may not be repairable. Safe activities and monitoring of meteor activity.
|  | SH-3.3 | Catastropic Depressurization | 1 | 5 | 5 | Obeying maximum system habitats, designing habitat to deal with minor meteoroids, monitoring substantial meteorite activity. Drills to rapidly close doors in case of event.
SH-4 | Airlock Door Jamming |  |  |  |  | 0
|  | SH-4.1 | Failure to Close | 3 | 2 | 6 | Proper maintenance of door's moving parts and mechanisms
|  | SH-4.2 | Failure to Open | 3 | 2 | 6 | Proper maintenance of door's moving parts and mechanisms
SH-5 | Airlock Fireproof Failure |  |  |  |  | 0
|  | SH-5.1 | Fire jumps across closed door | 2 | 4 | 8 | Proper maintenance and replacement of fireproof seals on airlock door. Testing of doors on Earth for fire resistance.
SH-6 | Airlock Airtight Failure |  |  |  |  | 0
|  | SH-5.2 | Failure to contain depressurization | 1 | 5 | 5 | Proper maintenance of airlock doors, testing on Earth to ensure functionality
SH-7 | Structural Failure |  |  |  |  | 0
|  | SH-7.1 | Regolith cage bends | 2 | 1 | 2 | Stress sensors added to the structure to monitor real-time stresses
|  | SH-7.2 | Regolith cage punctures habitat | 1 | 3 | 3 | Monitor stress sensors, Check to ensure within acceptable tolerances, measure height of structure
|  | SH-7.3 | Regolith cage blocks exit | 1 | 1 | 1 | Use other exits to mitigate, Warning includes bending of the structure and higher stress tolerances
|  | SH-7.4 | Regolith cage damages ECLSS system | 1 | 1 | 1 | Backup or additional ECLSS system components fulfill the role of the missing ECLSS system component.
SH-8 | Assembly Failure on Moon | SH-8.1 | Fabric tears during unpacking | 1 | 4 | 4 | Live in other habitats if possible, potentially catastrophic if all modules are destroyed
|  | SH-8.2 | Interlocking components are not machined correctly | 1 | 5 | 5 | Live in existing Starship module for as long as possible, Attempt to assemble regardless of compoent interlocking concerns. Potentially inflate habitats by themselves instead of connecting them.
|  | SH-8.3 | Crane cannot lift habitats from starship | 1 | 4 | 4 | Live in existing starship, Monitor and assess all available resources, attempt to deploy habitats using secondary deployment method
SH-9 | Radiation Shield Failure | SH-9.1 | Radiation detected within crew quarters | 1 | 3 | 3 | Move crew to living in other modules where radiation was not detected, isolate module from habitat system
|  | SH-9.2 | Radiation detected in lab module | 1 | 3 | 3 | Note results of experiments may be affected, limit crew exposure in the module
|  | SH-9.3 | Radiation detected within food | 1 | 4 | 4 | Test amount of radiation, (depending on amount) prepare emergency return to earth
SH-10 | Tripping Hazards |  |  |  |  | 0
|  | SH-10.1 | Floor debris and tripping hazards present | 4 | 1 | 4 | Strict adherence to OSHA standards for tripping hazards. Basic medical equipment present for treating sprains, stabilizing more serious injuries such as breaks.
SH-11 | Fire Suppression System Failure |  |  |  |  | 0
|  | SH-11.1 | Failure to detect fire | 1 | 5 | 5 | Regular inspection and testing of fire detection system. Built in redundancy. Manual activation of fire suppression system.
|  | SH-11.2 | Failure to deploy | 1 | 5 | 5 | Regular inspeaction and maintenance of fire suppression system. Built-in sprinkler redundancy and parallel deployment architecture. Presence of manually operated fire suppression equipment.

## Life Support
Ref ID |  | Ref ID |  | Likelihood | Consequence | Overall | Mitigation/Warning | Post-Mitigation
| Intermediate Event |  | Basic Event |  |  |  |  | Likelihood | Consequence
SL-1 | Carbon Dioxide Buildup | SL-1.1 | Bosch Reactor Shutdown | 5 | 2 | 10 | Pre-planned maintenance,
|  | SL-1.2 | Catalyst Failure | 3 | 2 | 6 | Replace catalyst within Bosch reactor during routine maintenance.
|  | SL-1.3 | Air leak | 3 | 3 | 9 | Multiple ducts for each habitat, allowing partial draining
|  | SL-1.4 | Pump failure | 4 | 2 | 8 | Multiple pumps, self contained habitats
SL-2 | Trace Gas Contamination | SL-2.1 | Contaminant Control Failure | 3 | 2 | 6 | Modular habitats each contain their own trace gas control system.
SL-3 | Particulate Contamination | SL-3.1 | Filter failure | 3 | 4 | 12 | Each habitat contains seperate filtration systems. Wear respirators while reparing damaged filters.
|  | SL-3.2 | Particulate buildup | 5 | 2 | 10 | Clean filters regularly
|  | SL-3.3 | Power Loss | 2 | 2 | 4 | Monitor electrical systems, restore power to oxygen regeneration/filtration system before any other systems.
SL-4 | Pump Failure | SL-1.4.1 | Electrical Failure | 2 | 2 | 4 | Repair or replace pump. Modular design mitigates risk.
|  | SL-1.4.2 | Mechanical Failure | 2 | 2 | 4 | Repair or replace pump. Modular design mitigates risk.
|  | SL-1.4.3 | Power loss | 3 | 2 | 6 | Restore power to pumps
SL-5 | Bosch Reactor Shutdown | SL-1.1.1 | Boudard reaction failure | 1 | 2 | 2 | CO is not converted into CO2, leading to a failure within the Bosch reaction. Inspect system during maintenance.
|  | SL-1.1.2 | Bosch reaction failure | 1 | 2 | 2 | CO2 is not converted into H2O and C, either due to a loss of catalyst or any other cascading fault. Inspect during maintenance.
|  | SL-1.1.3 | Water removal failure | 1 | 3 | 3 | Water removal system fails, due to a pump failure, loss of pressure, etc. Shut down reactor, repair, and inspect during routine maintenance.
|  | SL-1.1.4 | Loss of power | 3 | 2 | 6 | Return power to system, inspect during maintenance.
|  | SL-1.1.5 | Loss of heat | 3 | 2 | 6 | Inspect during maintenance, shut down reactor, and restart heating element.
SL-6 | Waste Management Failure | SL-4.1 | Urine Recycling Failure | 2 | 2 | 4 | If failure occurs, urine recycling will be temporarily shut down until fixed. Colonists would have to obtain water elsewhere.
|  | SL-4.2 | Solide Waste Digestion Failure | 1 | 2 | 2 | If failure occurs, possible overflow of human waste in colony. Production of methane gas comes to a halt
|  | SL-4.3 | Water Recover Failure | 2 | 2 | 4 | If the water recovery system fails, colonists will have to rely on water reserves until repairs can be done.
SL-7 | Urine Recycling Failure | SL-4.1.1 | Power Loss | 3 | 2 | 6 | Address approriate power failure
|  | SL-4.1.2 | Pump Failure | 2 | 2 | 4 | Regularly maintain and clean urine processor assembly. Replace parts if necessary.
SL-8 | Solide Waste Digestion Failure | SL-4.2.1 | Power Loss | 3 | 2 | 6 | Batch is potentially ruined from the lack of heat required. Address appropriate power failure.
|  | SL-4.2.2 | Pump Failure | 2 | 4 | 8 | Potential buildup of methane gas. Problematic if inhaled and flamable. Regurlaly maintain and clean parts. Replace if necessary.
|  | SL-4.2.3 | Methane Reaction Failure | 2 | 1 | 2 | Possible issue with temperature regulation or microrbs in batch. Check possible sources of failure and address appropriately.
SL-9 | Water Recovery Failure | SL-4.3.1 | Power Loss | 2 | 2 | 4 | There is contigency built in for a power loss where enough additional water will be present for colonist survival given the worst case scenario.
|  | SL-4.3.2 | Over Contamination | 1 | 2 | 2 | The recycled water could have above safe concentrations of urine brine, biocide, or other inorganic materials. This is a monitoring problem rather than a water supply issue. There is a control system in place to monitor water purity and samples are sent to earth for further testing.
SL-10 | ATCS Failure | SL-5.1 | Internal Loop Leak | 1 | 2 | 2 | The internal loop is within the pressurized module of that habitat and protected by the rigidized regolith layer and MLI making it extremely unlikely for a leak to occur due to MM/OD. The internal coolant (water) is non-toxic. If an internal loop leak were to occur, the pump would be shut down, pressure would vent from the loop, and the ATCS would fail over to the redundant loop.
|  | SL-5.2 | External Loop Leak | 2 | 4 | 8 | The external loop is mostly outside of the pressurized module and could be struck by MM/OD (most likely leak location would be through the radiators). If a leak were to occur where the external loop enters the habitat, the ammonia would present toxicity concerns. If a leak were to occur on the external loop the pump would be shut off and the ATCS would fail over to the redundant loop.
|  | SL-5.3 | IFHX Leak | 1 | 4 | 4 | The internal loop is within the pressurized module of that habitat and protected by the rigidized regolith layer and MLI making it extremely unlikely for a leak to occur due to MM/OD. A leak at this location would cause fluid mixing or ammonia (toxic) to enter the habitat. If a leak were to occur within the IFHX, both the connected internal and external pumps would be shut off and the ATCS would fail over to the redundant loops.
|  | SL-5.4 | Pump Failure | 2 | 2 | 4 | A pump failure at on either pump would result in loss of heat absorbtion/rejection capability. If a pump failure occurs, the ATCS fails over to the redundant loop.
|  | SL-5.5 | Loss of Power | 1 | 5 | 5 | Loss of power for the habitat is a catastrophic failure. If this were to occur, the habitat fails over to redundant power source.
|  | SL-5.6 | Coolant Loop Freeze/Overpressurization | 2 | 3 | 6 | Freezing of the external coolant loops results from fluid dropping below its operating temperature limit. This is prevented by adding resistive operational heaters to all external coolant loop lines which activate when the fluid temperature drops below a specified threshold.
|  | SL-5.7 | Heater Switch Failure | 2 | 3 | 6 | The switches that activate or deactivate heaters can fail either ON or OFF resulting in heat when no heat is needed or no heat when heat is needed. This is prevented by having two switches in series such that if one switch fails ON, the other switch can be opened for prevent heat and vice versa. That heater line is marked as failed and the ATCS then fails over to the redudant heater line.

## Agriculture
Ref ID |  | Ref ID |  |  |  | Overall | Mitigation/Warning | Post-Mitigation
| Intermediate Event |  | Basic Event | Likelihood | Consequence |  |  | Likelihood | Consequence
SA-1 | Light System Failure | SA-1.1 | Light Bulb Failure | 1 | 3 | 3 | Parallel Wiring design, Replace Light bulbs when near end of design life | 1 | 3 | SA-1.1
|  | SA-1.2 | Electrical Wiring Failure | 2 | 3 | 6 | Ensure Wiring is robust to environmental conditions | 1 | 3 | SA-1.2
|  | SA-1.3 | [7 empty] | SA-1.3
SA-2 | Nozzle Control System Failure | SA-2.1 | Water Supply Failure | 1 | 4 | 4 | Check Water Supply levels; Investigate water Supply conneciton for signs of failure | 1 | 4 | SA-2.1
|  | SA-2.2 | Nutrient Spray Supply Failure | 2 | 3 | 6 | Check Nutrient Supply levels; Investigate Nutrient Supply conneciton for signs of failure | 1 | 4 | SA-2.2
|  | SA-2.3 | Nozzle Failure | 1 | 2 |  |  |  |  | SA-2.3
|  | SA-2.4 | Control Algorthim Failure | 1 | 4 |  | verify and validate code; Test Code in simulated environment | 1 | 4 | SA-2.4
SA-3 | Crop Failure | SA-3.1 | Loss of Plant Seeds | 1 | 3 | 3 | Ensure Seeds are kept in hospitable conditions, keep a redudent supply of seeds in case main group of seeds fail; Use different seed varieties | 1 | 1 | SA-3.1
|  | SA-3.2 | Plants Die Out | 1 | 4 | 4 |  |  |  | SA-3.2
SA-4 | Harvested Food failure | SA-4.1 | Harvested Food Spoils | 2 | 2 | 4 |  |  |  | SA-4.1
0
SA-5 | Thermal System Failure | SA-5.1 | Temperature Above Acceptable Levels | 1 | 3 | 3 | Use feedback control system to keep temeprature in acceptable level | 1 | 3 | SA-5.1
|  | SA-5.2 | Temperature Below Acceptable Levels | 1 | 3 | 3 | Use feedback control system to keep temeprature in acceptable level | 1 | 3 | SA-5.2
SA-6 | Aeroponic Tower Failure | SA-6.1 | Aeroponic Tower Collapses | 1 | 4 | 4 | Ensure structure has a high safety factror; Structure does not have a load higher than design for place on it | 1 | 4 | SA-6.1
|  | SA-6.2 | Aeroponic Tower Bends | 1 | 1 | 1 |  |  |  | SA-6.2

## Research Facilties
Ref ID |  | Ref ID |  | Likelihood | Consequence | Overall | Mitigation/Warning | Post-Mitigation
| Intermediate Event |  | Basic Event |  |  |  |  | Likelihood | Consequence
SR-1 | Power failure | SR-1.1 | Short circuit | 1 | 1 | 1 | Proper electrical maintenance, sensors to detect short | 1 | 1 | SR-1.1
|  | SR-1.2 | Solar panel failure | 1 | 1 | 1 | Redundant solar panels | 1 | 1 | SR-1.2
SR-2 | Sample collection failure | SR-2.1 | Incorrect container used | 1 | 2 | 2 | Proper labeling and storage | 1 | 2 | SR-2.1
|  | SR-2.2 | Sample incorrect patient | 1 | 2 | 2 | Proper labeling and storage | 1 | 2 | SR-2.2
|  | SR-2.3 | Broken test tube | 2 | 3 | 6 | Biohazard cleaning procedures | 1 | 3 | SR-2.3
SR-3 | Instrument failure | SR-3.1 | Component failure | 1 | 4 | 4 | Redundant maintenance and inspection | 1 | 4 | SR-3.1
|  | SR-3.2 | Unresponsive software | 1 | 1 | 1 | Reboot of system | 1 | 1 | SR-3.2
|  | SR-3.3 | Data loss | 1 | 4 | 4 | Cloud storage, frequent data backups | 1 | 2 | SR-3.3
SR-4 | Exercise equipment failure | SR-4.1 | Component failure | 2 | 4 | 8 | Thorough maintenance and inspection | 1 | 4 | SR-4.1
|  | SR-4.2 | Power loss | 1 | 3 | 3 | Backup battery power | 1 | 2 | SR-4.2
|  | SR-4.3 | Operator error | 2 | 2 | 4 | Proper training standards for crew and equipment | 1 | 2 | SR-4.3
|  | SR-4.4 | Programming failure | 1 | 3 | 3 | Error analysis of software, solution detection programming | 1 | 2 | SR-4.4
SR-5 | Improper lunar sample storage | SR-5.1 | Human negligence | 1 | 2 | 2 | Proper training for crew, sufficient storage space | 1 | 2 | SR-5.1
|  | SR-5.2 | Storage failure | 1 | 2 | 2 | Well-sealed storage containers | 1 | 2 | SR-5.2
|  | SR-5.3 | Sample volume error | 1 | 1 | 1 | Proper sample collection standards, proper training | 1 | 1 | SR-5.3

## Satellites
Ref ID |  | Likelihood | Consequence | Ref ID |  |  |  |  | Mitigation/Warning | Post-Mitigation
| Intermediate Event |  |  |  | Basic Event | Likelihood | Consequence | Overall |  | Likelihood | Consequence
VS-1 | No contact with communications satellite | 2 | 4 | OVS-1.1 | Transceiver failure | 1 | 4 | 4 | Redundant communications components implemented | 1 | 4 | OVS-1.1
|  |  |  | OVS-1.2 | Incorrect ground station configuration | 2 | 2 | 4 | Ground station can be reconfigured, operations procedures should be detailed and tested | 2 | 2 | OVS-1.2
|  |  |  | OVS-1.3 | Computer fault | 1 | 4 | 4 | Redundant C&DH system recommended | 1 | 3 | OVS-1.3
|  |  |  | OVS-3 | Solar panels do not provide power | 2 | 4 | 8 | See VS-3 | 2 | 5 | OVS-3
VS-2 | No contact with observation satellite | 1 | 4 | OVS-2.1 | Incorrect crosslinking configuration | 1 | 5 | 5 | Ensure correct configuration through testing. If incorrect, configuration can be fixed when Wheatley GS is built, but significant delay | 1 | 4 | OVS-2.1
|  |  |  | OVS-2.2 | Computer fault | 1 | 4 | 4 | Redundant C&DH system recommended | 1 | 3 | OVS-2.2
|  |  |  | OVS-3 | Solar panels do not provide power | 2 | 4 | 8 | See VS-3 | 2 | 5 | OVS-3
VS-3 | Solar panels do not provide power | 2 | 4 | OVS-3.1 | Solar panels do not deploy | 2 | 5 | 10 | Ensure through testing | 2 | 4 | OVS-3.1
|  |  |  | OVS-3.2 | Solar panel short | 1 | 5 | 5 | Implement low-power mode in attempt to save satellite if short occurs | 1 | 5 | OVS-3.2
|  |  |  | OVS-7 | Satellite has incorrect attitude | 1 | 3 | 3 | See VS-7 | 2 | 4 | OVS-7
VS-4 | Camera images are unusable (ie blurry, corrupted) | 1 | 4 | OVS-4.1 | Error in optics (ie misalignment) | 1 | 5 | 5 | Ensure through testing | 1 | 4 | OVS-4.1
|  |  |  | OVS-4.2 | Error in data management system | 1 | 4 | 4 | Redundant C&DH systems recommended, reset system if occurs | 1 | 3 | OVS-4.2
|  |  |  | OVS-7 | Incorrect attitude for image collection | 1 | 3 | 3 | See VS-7 | 2 | 4 | OVS-7
|  |  |  | OVS-9 | Off-nominal orbit | 1 | 3.5 | 3.5 | See VS-9 | 1 | 3 | OVS-9
VS-5 | Sensor data are unusable (ie unusual, corrupted) | 1 | 4 | OVS-5.1 | Error in instrumentation (ie uncalibrated) | 1 | 5 | 5 | Ensure through testing | 1 | 4 | OVS-5.1
|  |  |  | OVS-5.2 | Error in data management system | 1 | 4 | 4 | Redundant C&DH systems recommended, reset system if occurs | 1 | 3 | OVS-5.2
|  |  |  | OVS-7 | Incorrect attitude for data collection | 1 | 3 | 3 | See VS-7 | 2 | 4 | OVS-7
|  |  |  | OVS-9 | Off-nominal orbit | 1 | 3.5 | 3.5 | See VS-9 | 1 | 3 | OVS-9
VS-6 | Satellite does not successfully transmit data | 1 | 3 | OVS-6.1 | Error in data management system | 1 | 4 | 4 | Redundant C&DH systems recommended | 1 | 3 | OVS-6.1
|  |  |  | OVS-6.2 | Antenna not correctly aligned | 1 | 2 | 2 | Change attitude control of satellite to restore correct pointing | 1 | 2 | OVS-6.2
|  |  |  | OVS-6.3 | Incorrect communication system configuration | 1 | 3 | 3 | Configuration can be fixed | 1 | 3 | OVS-6.3
|  |  |  | OVS-7 | Pointing error due to incorrect attitude | 1 | 3 | 3 | See VS-7 | 2 | 4 | OVS-7
VS-7 | Satellite has incorrect attitude | 1 | 3 | OVS-7.1 | Reaction wheel component failure | 2 | 4 | 8 | Redundant RWA implemented | 2 | 3 | OVS-7.1
|  |  |  | OVS-7.2 | Attitude sensor malfunction (ie blocked or degraded) | 1 | 4 | 4 | Multiple sensors implemented but in case of event, investigate algorithms and alternate control modes to salvage control | 1 | 4 | OVS-7.2
|  |  |  | &VS-7.3 | Reaction wheels saturated | 1 | 1 | 1 | Desaturate RWA | 1 | 1 | &VS-7.3
|  |  |  | &VS-7.4 | ACS thruster failure | 1 | 3 | 3 | Investigate alternative thruster combos for desaturation and alternative control models | 1 | 3 | &VS-7.4
VS-8 | Battery failure | 1 | 5 | OVS-8.1 | Battery cell failure | 1 | 5 | 5 | Implement low-power mode to salvage mission | 1 | 5 | OVS-8.1
|  |  |  | OVS-8.2 | Charging failure | 1 | 5 | 5 | Implement low-power mode to salvage mission | 1 | 5 | OVS-8.2
|  |  |  | OVS-8.3 | Power distribution, computer failure | 1 | 4 | 4 | Implement contignency procedures | 1 | 4 | OVS-8.3
VS-9 | Off-nominal orbit | 1 | 4 | OVS-9.1 | Orbit determination system failure | 1 | 2 | 2 | Update algorithm | 1 | 2 | OVS-9.1
|  |  |  | OVS-9.2 | Propulsion system failure (chemical for comms, electric for obs) | 1 | 5 | 5 | Ensure through testing, redundancy, known good propulsion technology where redundancy isn't present (NSTAR) | 1 | 4 | OVS-9.2

## Rovers
Ref ID | Intermediate Event | Ref ID | Basic Event | Likelihood | Consequence | Overall | Mitigation/Warning | Post-Mitigation |  |  | Severity
MINING ROVER | [7 empty] | Likelihood | Consequence |  | 25
VRM-1 | Drive-train Failure | VRM-1.1 | broken steering linkage | 3 | 5 | 15 | Better surface surveillance | 1 | 5 | 5 | 20
|  | VRM-1.2 | dust in motor | 1 | 5 | 5 | Cover motor | 1 | 5 | 5 | 15
|  | VRM-1.3 | loss of motor power | 2 | 5 | 10 | backup power | 1 | 5 | 5 | 10
VRM-2 | Drill failure | VRM-2.1 | DC motor voltage spike | 1 | 1 | 1 | surge protector | 1 | 1 | 1 | 5
|  | VRM-2.2 | Dust jams drill drive gears | 2 | 5 | 10 | Cover gears | 1 | 5 | 5 | 0
|  | VRM-2.3 | Drill breaks from overuse | 3 | 3.5 | 10.5 | Extra drill tips/ reinforce drills | 1 | 3.5 | 3.5
|  | VRM-2.4 | Drill overheats and melts | 1 | 3.5 | 3.5 | Temperature sensors, stop drilling when too hot | 1 | 3.5 | 3.5
VRM-3 | Storage failure | VRM-3.1 | Blockage in storage bay prevents further loading | 3 | 2 | 6 | Use ERAs to unblock storage bay, don't load when storage bay reaches maximum capacity | 2 | 2 | 4
|  | VRM-3.2 | ERAs fail to maneuver core into bay | 2 | 1 | 2 | Better controls code | 1 | 1 | 1
|  | VRM-3.3 | storage bay is overfilled | 2 | 1 | 2 | Prevent this from happening in code with simple if statement | 1 | 1 | 1
|  | VRM-3.4 | storage bay is compromised by impact | 1 | 4 | 4 | reinforce storage bay with titanium lining | 1 | 3 | 3
VRM-4 | Instrumentation failure | VRM-4.1 | Imaging/camera failure | 1 | 2.5 | 2.5 | Replacement camera parts kept at base | 1 | 2 | 2
|  | VRM-4.2 | Loss of attitude knowledge | 1 | 2 | 2 | Backup information based on last known attitude | 1 | 2 | 2
|  | VRM-4.4 | Loss of position knowledge | 2 | 2 | 4 | Backup information based on last known location | 2 | 2 | 4
VRM-5 | Battery Failure | VRM-5.1 | Voltage surge due to solar flare | 2 | 3.5 | 7 | Solar ray protection for electronics | 1 | 3.5 | 3.5
|  | VRM-5.2 | Battery overheats | 1 | 2 | 2 | Temperature warning for high heat in battery area | 1 | 2 | 2
|  | VRM-5.3 | Battery discharges completely | 2 | 2.8 | 5.6 | Warning for irregular battery discharge rates | 1 | 2.8 | 2.8
|  | VRM-5.4 | Electrical connection loss | 1 | 3 | 3 | Warning when power lost | 1 | 3 | 3
|  | VRM-5.5 |  |  |  | 0 |  |  |  | 0
VRM-6 | Structural Failure | VRM-6.1 | Failure of floor of storage bay | 1 | 3.8 | 3.8 | Reinforce storage bay floor/have replacement floor on hand | 1 | 2.5 | 2.5
|  | VRM-6.2 | Suspension failure due to overload | 2 | 2.6 | 5.2 | Clean out storage bay material accumulation regularly | 1 | 2.6 | 2.6
|  | VRM-6.3 | Wheel failure due to overload | 2 | 2.2 | 4.4 | Clean out storage bay material accumulation regularly | 1 | 2.2 | 2.2
|  | VRM-6.4 | ERA failure due to overload | 2 | 3.4 | 6.8 | Clean out storage bay material accumulation regularly | 1 | 3.4 | 3.4
VRM-7 | Suspension Failure | VRM-7.1 | Jammed suspension | 4 | 2 | 8 | Object detection for suspension clearing issues | 2 | 2 | 4
VRM-8 | Loss of Stability | VRM-8.1 | Tipping/falling | 3 | 4 | 12 | Onboard emergency programming for arm usage to assist rover | 2 | 2 | 4
|  | VRM-8.2 | Loss of ERA attitude knowledge | 2 | 1.2 | 2.4 | Backup information based on last known attitude | 2 | 1.2 | 2.4
|  | VRM-8.3 | Loss of vehicle attitude knowledge | 2 | 1.2 | 2.4 | Backup information based on last known attitude | 2 | 1.2 | 2.4
SCOUTING ROVER
VRS-1 | Drive-train Failure | VRS-1.1 | Dust jams DC motor | 2 | 5 | 10 | Cover motor | 1 | 5 | 5
|  | VRS-1.2 | DC motor overheat | 1 | 3 | 3 | Temperature sensors, stop usage when too hot | 1 | 3 | 3
VRS-2 | Instrumentation Failure | VRS-2.1 | Loss of position knowledge | 2 | 2 | 4 | Redundant Star Trackers/ Reposition using RF beacons | 1 | 2 | 2
|  | VRS-2.2 | Imaging/camera failure | 2 | 2.5 | 5 | Redundant camera Reposition using RF beacons | 1 | 2.5 | 2.5
|  | VRS-2.3 | Radiation damage | 2 | 3 | 6 | Warning: Bit-flips, computing glitches. Mitigation: shielding | 1 | 3 | 3
VRS-3 | Battery failure | VRS-3.1 | Battery death | 2 | 5 | 10 | Warning: Notify base when at 20%. Mitigation: charge battery | 1 | 5 | 5
|  | VRS-3.2 | Battery Overheat | 1 | 3 | 3 | TCS, temperature sensors, stop usage when too hot | 0.5 | 3 | 1.5
VRS-4 | Structural failure | VRS-4.4 | Impact damage | 2 | 3 | 6 | Impact testing | 2 | 3 | 6
|  | VRS-4.5 | Wheel nut failure | 1 | 3 | 3 | Warning: Strain gage reading | 0.5 | 3 | 1.5
VRS-5 | Suspension failure | VRS-5.1 | Tipping/falling | 2 | 3 | 6 | Vertical axis of vehicle becomes parallel to surface, Mitigation: use arm to stabilize | 1 | 2 | 2
|  | VRS-5.2 | Suspension breakage | 1 | 5 | 5 | Warning: Strain gage reading | 0.5 | 5 | 2.5
CLEARING ROVER
VRC-1 | Drive Train Failure | VRC-1.1 | Broken Steering Linkage | 3 | 4 | 12 | Better surface surveillance | 1 | 5 | 5
|  | VRC-1.2 | Dust in Motor | 1 | 1 | 1 | Cover motor | 1 | 5 | 5
|  | VRC-1.3 | Loss of Motor Power | 2 | 5 | 10 | backup power | 1 | 5 | 5
VRC-2 | Body Failure | VRC-2.1 | Body Buckles | 1 | 4 | 4 | Stress testing, reinforce with titanium | 0.5 | 4 | 2
|  | VRC-2.2 | Micrometeoroid Impacts | 4 | 2 | 8 | Impact Testing, reinforce with titanium | 4 | 1 | 4
VRC-3 | Instrument Failure | VRC-3.1 | GPS Position Loss | 2 | 2 | 4 | Warning sent through beacon system | 1 | 2 | 2
|  | VRC-3.2 | Solar Flare Interference | 1 | 3 | 3 | NASA Solar Flare detection warning | 1 | 2 | 2
|  | VRC-3.3 | Solar Wind Circuit Ionization | 2 | 3 | 6 | Radiation shield around sensitive electronics | 1 | 3 | 3
VRC-4 | Battery Failure | VRC-4.1 | Battery Explosion | 2 | 5 | 10 | Thermally stable enviornment in rover and temp warning | 1 | 4 | 4
|  | VRC-4.2 | Battery Recharge Failure | 2 | 4 | 8 | Warning on low power, backup circuit | 2 | 2 | 4
VRC-5 | Suspension Failure | VRC-5.1 | Fatigue Failure | 2 | 4 | 8 | stress testing to know when to replace | 1 | 3 | 3
VRC-6 | Robotic Arm Failure | VRC-6.1 | Robotic Arm Jam | 2 | 4 | 8 | Frequent Lubrication and angle limits to prevent jamming | 1 | 3 | 3
|  | VRC-6.2 | Robotic Arm Claw Failure | 1 | 3 | 3 | Better control code | 0.5 | 3 | 1.5
VRC-7 | Wheel Failure | VRC-7.1 | Wheel Bearing Jam | 2 | 3 | 6 | Frequent Lubrication | 1 | 3 | 3
|  | VRC-7.2 | Wheel Fatigue Failure | 1 | 4 | 4 | stress testing to know when to replace | 1 | 3 | 3
|  | VRC-7.3 | Spoke Failure | 1 | 4 | 4 | reinforce spokes with titanium | 0.5 | 4 | 2
VRC-8 | Axle Failure | VRC-8.1 | Fatigue Failure | 1 | 5 | 5 | stress testing to know when to replace | 1 | 3 | 3
VRC-9 | Plow Failure | VRC-9.1 | Plow Hydraulics Failure | 2 | 5 | 10 | Low pressure sensor warning | 1 | 5 | 5
VRC-10 | Auger Failure | VRC-10.1 | Augur Jam | 3 | 3 | 9 | Reverse auger/kill power if jammed both ways, alert ground crew | 2 | 1 | 2
COLLECTION ROVER
VRL-1 | Drive Train Failure | VRL-1.1 | Broken Steering Linkage | 3 | 4 | 12 | Better surface surveillance | 1 | 5 | 5
|  | VRL-1.2 | Dust in Motor | 1 | 1 | 1 | Cover motor | 1 | 5 | 5
|  | VRL-1.3 | Loss of Motor Power | 2 | 5 | 10 | backup power | 1 | 5 | 5
VRL-2 | Body Failure | VRL-2.1 | Body Buckles | 1 | 4 | 4 | Stress testing | 1 | 4 | 4
|  | VRL-2.2 | Micrometeoroid Impacts | 2 | 2 | 4 | Impact Testing | 1 | 2 | 2
VRL-3 | Instrument Failure | VRL-3.1 | GPS Position Loss | 2 | 2 | 4 | Reposition using RF beacons | 1 | 1.5 | 1.5
|  | VRL-3.2 | Solar Flare Interference | 1 | 3 | 3 | NASA Solar Flare detection warning | 1 | 3 | 3
|  | VRL-3.3 | Solar Wind Circuit Ionization | 2 | 3 | 6 | Radiation shield around sensitive electronics | 1 | 4 | 4
VRL-4 | Battery Failure | VRL-4.1 | Battery Explosion | 1 | 5 | 5 | Thermally stable enviornment in rover and temp warning | 1 | 2 | 2
|  | VRL-4.2 | Battery Recharge Failure | 2 | 4 | 8 | Warning on low power, backup circuit | 1 | 5 | 5
VRL-5 | Suspension Failure | VRL-5.1 | Fatigue Failure | 2 | 4 | 8 | Fatigue Testing | 1 | 4 | 4
VRL-6 | Robotic Arm Failure | VRL-6.1 | Robotic Arm Jam | 2 | 4 | 8 | Torque Sensor | 2 | 2 | 4
|  | VRL-6.2 | Robotic Arm Claw Failure | 1 | 3 | 3 | Effective Materials | 1 | 2 | 2
VRL-7 | Wheel Failure | VRL-7.1 | Wheel Bearing Jam | 2 | 3 | 6 | Torque Sensor | 1 | 2 | 2
|  | VRL-7.2 | Wheel Fatigue Failure | 1 | 4 | 4 | Fatigue Testing | 1 | 4 | 4
|  | VRL-7.3 | Spoke Failure | 1 | 4 | 4 | Stress testing | 1 | 4 | 4
VRL-8 | Axle Failure | VRL-8.1 | Fatigue Failure | 1 | 5 | 5 | Fatigue Testing | 1 | 5 | 5
VRL-9 | Storage Failure | VRL-9.1 | Bay Door Jamming | 2 | 5 | 10 | Dust Blocker | 1.5 | 4 | 6
|  | VRL-9.2 | Storage Enterence Bloackage | 2 | 4 | 8 | Locking sensor on storage bay entrance | 2 | 4 | 8
VRL-10 | Collection Rig Failure
CONSTRUCTION/MODULAR ROVER
VRD-1 | Drivetrain failure | VRD-1.1 | Dust in DC motor | 1 | 4 | 4 | Cover motor | 1 | 5 | 5
|  | VRD-1.2 | Broken Steering Linkage | 3 | 1 | 3 | Better surface surveillance | 1 | 5 | 5
|  | VRD-1.3 | Loss of motor power | 2 | 5 | 10 | backup power | 1 | 5 | 5
VRD-2 | Body Failure | VRD-2.1 | Body Buckles | 1 | 4 | 4 | reinforce body with titanium lining | 1 | 3 | 3
|  | VRD-2.2 | Micrometeroid impacts | 2 | 2 | 4 | extra protection of key areas | 2 | 1 | 2
VRD-3 | Instrumentation Failure | VRD-3.1 | GPS Position Loss | 2 | 2 | 4 | Backup location data based on last position/use instruments | 2 | 1.5 | 3
|  | VRD-3.2 | Solar Flare Interference | 2 | 3.5 | 7 | Solar ray protection for electronics | 1 | 3.5 | 3.5
|  | VRD-3.3 | Solar Wind Circuit Ionization | 2 | 2 | 4 | Radiation shielding | 1 | 2 | 2
VRD-4 | Battery Failure | VRD-4.1 | Battery Explosion | 1 | 4 | 4 | Shielding around battery, replacement battery on site | 1 | 2 | 2
|  | VRD-4.2 | Battery Recharge Failure | 1 | 3 | 3 | have light or sensor to indicate when battery is not charging so problem can be fixed immediately | 0.5 | 3 | 1.5
VRD-5 | Suspension Failure | VRD-5.1 | Fatigue Failure | 2 | 3 | 6 | cycle testing prior to launch to know when to replace suspension | 1 | 3 | 3
|  | VRD-5.2 | Shock/Impact Failure | 1 | 2 | 2 | reinforce with titanium | 1 | 1 | 1
|  | VRD-5.3 | Detachment | 1 | 1 | 1 | reinforce attachment points | 0.5 | 0.5 | 0.25
VRD-6 | Wheel Failure | VRD-6.1 | Impact Damage | 1 | 5 | 5 | reinforce body with titanium lining | 1 | 3 | 3

## PropulsionMission Design
Ref ID |  | Ref ID |  | Likelihood | Consequence | Overall | Mitigation/Warning | Post-Mitigation
| Intermediate Event |  | Basic Event |  |  |  |  | Likelihood | Consequence
STARSHIP
PR-1 | Unable to reach LEO | PR-1.1 | Structural Failure | 1 | 5 | 5 | Rigorous structural tests before approved as launch vehicle | 1 | 5
|  | PR-1.2 | Engine Failure | 1 | 5 | 5 | Engine Tests immediately leading up to launch | 1 | 5
|  | PR-1.3 | Separation Failure | 1 | 5 | 5 | Inspect interstage components before launch | 1 | 5
|  | PR-1.4 | Navigation Failure | 1 | 5 | 5 | Install secondary backup navigation system with additional fuel for trajectory corrections | 1 | 5
PR-2 | Unable to reach LLO | PR-2.1 | Structural Failure | 1 | 5 | 5 | Rigorous structural tests before approved as launch vehicle | 1 | 5
|  | PR-2.2 | Engine Failure | 1 | 5 | 5 | Engine Tests immediately leading up to launch | 1 | 5
|  | PR-2.3 | Separation Failure | 1 | 5 | 5 | Inspect interstage components before launch | 1 | 5
|  | PR-2.4 | Navigation Failure | 1 | 5 | 5 | Install secondary backup navigation system and include additional fuel for trajectory corrections | 1 | 5
|  | PR-2.5 | LEO Refueling Failure | 3 | 5 | 15 | Multiple refueling test maneuvers before introduction of LEO fuel depot into mission with additional fuel for RCS orientation correction | 1 | 5
PR-3 | Unable to reach lunar surface | PR-3.1 | Structural Failure | 1 | 5 | 5 | Rigorous structural tests before approved as launch vehicle | 1 | 5
|  | PR-3.2 | Engine Failure | 1 | 5 | 5 | Engine Tests immediately leading up to launch | 1 | 5
|  | PR-3.3 | Navigation Failure | 1 | 5 | 5 | Install secondary backup navigation system with additional fuel for trajectory corrections | 1 | 5
|  | PR-3.4 | Human Landing System Failure | 1 | 5 | 5 | Inspection of human landing system (HLS) and multiple holistic tests ranging from launch/landing to pressurization and crew needs | 1 | 5
|  | PR-3.5 | LEO Refueling Failure | 3 | 5 | 15 | Multiple refueling test maneuvers with additional fuel for RCS orientation correction | 1 | 5
|  | PR-3.6 | LLO Refueling Failure | 3 | 5 | 15 | Multiple refueling test maneuvers with additional fuel for RCS orientation correction | 1 | 5
PR-4 | Failure to safely land on lunar surface | PR-4.1 | Structural Failure | 1 | 5 | 5 | Rigorous structural tests conducted on landing legs on earth before launch | 1 | 5
|  | PR-4.2 | Engine Failure | 1 | 5 | 5 | Engine Tests immediately leading up to launch | 1 | 5
|  | PR-4.3 | Navigation Failure | 1 | 5 | 5 | Install multiple cameras for landing to mitigate lunar regolith damage to navigation systems | 1 | 5
|  | PR-4.4 | Human Landing System Failure | 1 | 5 | 5 | Inspection of human landing system (HLS) and multiple holistic tests ranging from launch/landing to pressurization and crew needs | 1 | 5
PR-5 | Failure to safely ascend from lunar surface | PR-5.1 | Structural Failure | 1 | 5 | 5 | Rigorous structural tests conducted on landing legs on earth before launch | 1 | 5
|  | PR-5.2 | Engine Failure | 1 | 5 | 5 | Engine Tests immediately leading up to launch | 1 | 5
|  | PR-5.3 | Navigation Failure | 1 | 5 | 5 | Install multiple cameras for landing to mitigate lunar regolith damage to navigation systems | 1 | 5
|  | PR-5.4 | Human Landing System Failure | 1 | 5 | 5 | Inspection of human landing system (HLS) and multiple holistic tests ranging from launch/landing to pressurization and crew needs | 1 | 5
PR-6 | Unable to return to Earth orbit | PR-6.1 | Structural Failure | 1 | 5 | 5 | Rigorous structural tests before approved as launch vehicle | 1 | 5
|  | PR-6.2 | Engine Failure | 1 | 5 | 5 | Engine Tests immediately leading up to launch | 1 | 5
|  | PR-6.3 | Navigation Failure | 1 | 5 | 5 | Install secondary backup navigation system with additional fuel for trajectory corrections | 1 | 5
|  | PR-6.5 | LEO Refueling Failure | 3 | 5 | 15 | Multiple refueling test maneuvers with additional fuel for RCS orientation correction | 1 | 5
|  | PR-6.6 | LLO Refueling Failure | 3 | 5 | 15 | Multiple refueling test maneuvers with additional fuel for RCS orientation correction | 1 | 5
PR-7 | Failure to safely land on Earth surface | PR-4.1 | Structural Failure | 1 | 5 | 5 | Rigorous structural tests conducted on landing legs on earth before launch | 1 | 5
|  | PR-4.2 | Engine Failure | 1 | 5 | 5 | Engine Tests immediately leading up to launch | 1 | 5
|  | PR-4.3 | Navigation Failure | 1 | 5 | 5 | Install multiple cameras for landing to mitigate reentry damage to navigation systems | 1 | 5
|  | PR-4.4 | Heat Shielding Failure | 2 | 5 | 10 | Rigorous inspection of heat shiielding before launch from Earth and before return to Earth | 1 | 5
Falcon 9 Heavy
PR-5 | Unable to reach LEO | PR-5.1 | Structural Failure | 1 | 5 | 5 | Rigorous structural tests before approved as launch vehicle | 1 | 5
|  | PR-5.2 | Engine Failure | 1 | 5 | 5 | Engine Tests immediately leading up to launch | 1 | 5
|  | PR-5.3 | Separation Failure | 1 | 5 | 5 | Inspect interstage components before launch | 1 | 5
|  | PR-5.4 | Navigation Failure | 1 | 5 | 5 | Install secondary backup navigation system with additional fuel for trajectory corrections | 1 | 5
PR-6 | Unable to reach LLO | PR-6.1 | Structural Failure | 1 | 5 | 5 | Rigorous structural tests before approved as launch vehicle | 1 | 5
|  | PR-6.2 | Engine Failure | 1 | 5 | 5 | Engine Tests immediately leading up to launch | 1 | 5
|  | PR-6.3 | Separation Failure | 1 | 5 | 5 | Inspect interstage components before launch | 1 | 5
|  | PR-6.4 | Navigation Failure | 1 | 5 | 5 | Install secondary backup navigation system and include additional fuel for trajectory corrections | 1 | 5
|  | PR-6.5 | LEO Refueling Failure | 3 | 5 | 15 | Multiple refueling test maneuvers before introduction of LEO fuel depot into mission with additional fuel for RCS orientation correction | 1 | 5

## Communications
Ref ID |  | Likelihood | Consequence | Ref ID |  |  |  |  | Mitigation/Warning | Post-Mitigation
| Intermediate Event |  |  |  | Basic Event | Likelihood | Consequence | Overall |  | Likelihood | Consequence
CM-1 | No contact with Earth from Moon ground | 1 | 4 | OCM-1.1 | Wheatley Station Earth (WSE) transmitter is down | 1 | 3 | 3 | Accessible placement for easy repair, redundant transmitter if possible | 1 | 2 | OCM-1.1
|  |  |  | OCM-1.2 | WSE antenna is down | 1 | 3 | 3 | Accessible placement for east repair | 1 | 2 | OCM-1.2
0
CM-2 | No contact with CHELL constellation | 1 | 3 | OCM-2.1 | Wheatley Station Satellite (WSS) transmitter is down | 1 | 3 | 3 | Accessible placement for easy repair, redundant transmitter if possible | 1 | 2 | OCM-2.1
|  |  |  | OCM-2.2 | WSS antenna is down | 1 | 3 | 3 | Accessible placement for east repair | 1 | 2 | OCM-2.2
CM-3 | Images not successfully crosslinked between Imaging Sat and CHELL | 2 | 2 | OCM-3.1 | Imaging sat transmitter broken | 2 | 2 | 4 | commands and telemetry | 1 | 2 | OCM-3.1
|  |  |  | OCM-3.2 | CHELL reciever broken | 2 | 2 | 4 | CHELL can recieve in S and X bands | 1 | 2 | OCM-3.2
|  |  |  | OCM-3.3 | imaging sat antenna broken | 2 | 2 | 4 | downlink images to moon ground instead | 1 | 2 | OCM-3.3
|  |  |  | OCM-3.4 | CHELL antenna broken | 2 | 2 | 4 | uplink images from moon ground instead | 1 | 2 | OCM-3.4
CM-4 | Reduced DMR Connectivity | 4 | 3 | OCM-4.1 | An individual handheld radio is broken or dead | 1 | 2 | 2 | easy repair | 1 | 1 | OCM-4.1
|  |  |  | OCM-4.2 | Rover radio is broken or dead | 2 | 2 | 4 | easy repair | 1 | 1 | OCM-4.2
|  |  |  | OCM-4.3 | Repeater unit(s) broken or dead | 2 | 3 | 6 | easy repair | 1 | 1 | OCM-4.3
|  |  |  | OCM-4.4 | Base Station down | 1 | 4 | 4 | easy repair | 1 | 1 | OCM-4.4
CM-5 | Reduced Wi-Fi Connectivity | 4 | 3 | OCM-5.1 | Access Point broken or dead | 3 | 2 | 6 | very easy repair | 2 | 1 | OCM-5.1
|  |  |  | OCM-5.2 | worn cable at some point in the network | 3 | 2 | 6 | easy repair and/or replacement | 2 | 1 | OCM-5.2
|  |  |  | OCM-5.3 | base station down | 1 | 4 | 4 | easy repair | 1 | 2 | OCM-5.3